PLI Leadership Project Plan 2013/2014

Anne-Marie Young

Project #1 Special Education Professional Developments

“Shine a Light on Social Emotional Issues Impacting Students with Disabilities”

STANDARDS ADDRESSED: 1.1, 1.2, 1.3 ,2.1, 2.2, 2.3, 2.4, 3.1, 3.2, 3.3, 3.4, 4.1, 5.1, 5.2, 5.3, 5.4, and 6.1

| Date | Time | Location | Attendees | Activities |
| --- | --- | --- | --- | --- |
| 12/12/13 | 2:45pm | PSW office | Teresa (PSW), Anne | Review plan, integrate neurological talking points onto project presentation PPT slides |
| 12/17/13 | 3:30pm | Room 5 | Julie (Principal), Mr. Sanchez (APEIS), Marisa (PLI Partner), Anne, Teresa (PSW), Angelica (School Psych.), (Nancy Paracini) | Present fieldwork plan to team |
| 1/6/13 | 10:00am | Online (email) | Anne, Teresa (PSW) | Create/review interview questions for students/parents & questions for teacher survey |
| 1/6/13 | 6:00pm | Online (Email) | Anne/Jeanette (Coordinator) | Submit interview questions for students/parents & questions for teacher survey for review and feedback from an uninvolved professional |
| 1/8/13 | 10:00am | Coffee Table (Eagle Rock) | Anne/Teresa (PSW) | Create prompts for case studies |
| 1/17/14 | 8:30am | Room 4 | Anne/Teresa (PSW) | Conduct initial student interviews |
| 1/17/14 | 2:45pm | Room 8 | Mr. Sanchez (APEIS), Marisa (PLI Partner), Anne, Teresa (PSW), Angelica (School Pyche)/Analyze outcomes of initial student interviews with Teresa | Review plan for PD on 1/21/14 |
| 1/21/14 | 1:30pm | Room 46 | Mr. Sanchez (APEIS), Marisa (PLI Partner), Anne, Teresa (PSW), Angelica (School Psych.) | Conduct PD1 for teachers “Looking at the Roots of Special Education” Present fieldwork plan to teachers |
| 1/21/14 | 3:30pm | Room 46 | Susie Navarro (1st grade teacher)/Anne | Peer debrief with uninvolved professional |
| 1/21/14 | 3:45pm | Room 5 | Teresa (PSW)/Anne | Review field notes |
| 2/4/14 | 3:30pm | PSW’s office | Anne/Tersa(PSW) | Finalize case studies notes |
| 2/7/14 | 8:30am | Room 4/PSW’s office | Anne/Teresa (PSW) | Conduct initial parent interviews |
| 2/7/14 | 2:45pm | Room 8 | Anne/Marisa (PLI partner) Teresa (PSW)/Angelica (School Psych.) | Plan for PD 2: Building Awareness of Special Ed. at Plasencia Analyze outcomes of initial parent interviews and teacher surveys |
| 2/18/14 | 1:30pm | Room 46 | Anne/Marisa (PLI partner), Mr. Sanchez (APEIS) Teresa (PSW) | Conduct PD 2 for teachers “Building Awareness of Special Education at Plasencia” |
| 2/18/14 | 3:30pm | Room 46 | Susie Navarro (1st grade teacher /Anne | Peer debrief with uninvolved professional |
| 2/18/14 | 3:45pm | Room 5 | Anne/Teresa (PSW) | Review field notes |
| 3/7/14 | 2:30pm | Room 8 | Mr. Sanchez (APEIS), Anne, Teresa (PSW), | Plan for PD 3: Signs and Signals/Reactions to Trauma and Increasing Social/Emotional Understanding through Cum Explorations and Case Study Inquiries |
| 3/25/14 | 8:00am | Principal’s Office | Anne/Mr. Hernandez (Interim Principal) | Start office discipline referral data cycle |
| 3/25/14 | 1:30pm | Room 46 | Anne/Marisa (PLI partner)/Teresa (PSW)/Angelica (School Psych.)/Mr. Sanchez (APEIS) | Conduct PD 3: Signs and Signals/Reactions to Trauma and Increasing Social/Emotional Understanding through Cum Explorations and Case Study Inquiries (Initial Quick Write) |
| 3/25/14 | 3:30pm | Room 46 | Susie Navarro (1st grade teacher/Anne | Peer debrief with uninvolved professional |
| 3/25/14 | 3:45pm | Room 5 | Teresa (PSW)/Anne | Review field notes |
| 4/4/14 | 2:30pm | Room 8 | Mr. Sanchez (APEIS) Anne/ Teresa (PSW) | Plan for PD 4: Psychological 1st Aid/Teacher Self-Care/Case Study Findings in Summary |
| 4/7/14-4/11/14 | Various times | Room 4 | Anne/Teresa(PSW) | Continue with student interviews for students involved in case studies |
| 4/22/14 | 8:00am | Principal’s Office | Anne/Mr. Hernandez (interim principal) | Close office discipline referral data cycle/analyze data |
| 4/22/14 | 1:30pm | Room 46 | Mr. Sanchez (APEIS), Marisa (PLI Partner), Anne, Teresa (PSW), Angelica Contreras (school psychologist) | Conduct PD 4: Psychological 1st Aid/Teacher Self-Care/Case Study Findings in Summary/Student Interview Results (final quick write with share out and group discussions) |
| 4/22/14 | 3:30pm | Room 46 | Susie Navarro (1st grade teacher)/ Anne | Peer debrief with uninvolved professional |
| 4/22/14 | 3:45pm | Room 5 | Teresa (PSW)/Anne | Review field notes |
| 5/2/14 | 2:45pm | Room 8 | Anne/ Teresa (PSW) | Analyze case study notes, final quick writes, and summation of peer debriefing information |
| 5/20/14 | 2:45pm | Room 8 | Mr. Sanchez (APEIS), Marisa (PLI Partner), Anne, Teresa (PSW), Angelica Contreras (School Psych.) | Present fieldwork report and outcomes to team/discuss plan to present fieldwork outcomes to teachers/create a broad plan for next school year’s Special Education PDs |

Project #2: Lead the 4th Grade/SDC Project Based Learning (PBL) Health & Wellness

| Major Activities To Be Accomplished | Timeline and Agreed Upon Evidence of Accomplishments | Standards Met |
| --- | --- | --- |
| Lead the 4th Grade/SDC Project Based Learning (PBL) Health & Wellness Plan the Big Ideas Differentiate Learning Create Presentations and Lesson Plans Organize Student Projects Into Smaller Parts Plan and Arrange Field Trips Create Project Benchmarks Connect with the Community (bring in speakers, visit farmer’s market) Plan for a Health and Wellness Fair (invite school, parents, and community) | Monthly Planning Meetings and Feedback Loop (Every second Wednesday between Jan. & April) Weekly PBL (Every Tuesday 9:30-11:00) | 2.3, 2.4, 3.1, 3.2, 4.2, 4.3, 5.4, 6.1 |

Project #3: Assistant Treasurer of Plasencia Math/ Science Magnet

| Major Activities To Be Accomplished | Timeline and Agreed Upon Evidence of Accomplishments | Standards Met |
| --- | --- | --- |
| Plan and schedule fundraising events Oversee that all funds from fundraising events are collected Budget for fieldtrips and class expenditures Account and organize incoming funds Make bi-monthly bank deposits Email Treasurer #2 with deposit information directly following deposit Give budget updates and account information at monthly magnet parent meetings | Fundraising Calendar (responsibilities distributed among grade level) Ongoing (8/13-6/14) Ongoing (8/13-6/14) Ongoing (8/13-6/14) 1st and 3rd Friday of each month or as needed Monthly, starting 9/20/2013 | 6.1, 6.2 6.1, 6.2 |

Project #4: Special Education Designee and SST Management

| Major Activities To Be Accomplished | Timeline and Agreed Upon Evidence of Accomplishments | Standards Met |
| --- | --- | --- |
| Student Success Team Communicate with teachers and review student data of BOY, MOY, & EOY assessments as well as ongoing assessments Present SST process to teachers (PD) Guide teachers in navigating SST process Tier 1: In-Class Observations (Assessment, intervention, collaboration) Tier 2: Teacher/parent/RTI teacher informal conference (review assessment results, intervention plan, effectiveness) Tier 3: Conduct SST meetings, review Tier 1 & Tier 2 outcomes, Plan further actions Oversee that Special Education paperwork is being distributed under Special Ed. guidelines Conduct IEP meetings as a Special Education Designee | 8/2013; 12/2013; 5/2014 1/21/14 Ongoing Ongoing (as needed) Ongoing (as needed) Approximately 1-4 times per week Ongoing (8/2012- 6/2013 As needed (8/2013-6/2014 | 3.4, 5.1, 6.1, 6.2 3.4, 5.1, 6.1, 6.2 |

Project #5: High School Volunteer Project

| Major Activities To Be Accomplished | Timeline and Agreed Upon Evidence of Accomplishments | Standards Met |
| --- | --- | --- |
| Communicate with coordinators of New Village Girl’s Academy Arrange times for high school volunteers to meet the teachers that they will be working with Set up contact information with the high school volunteers’ coordinators Communicate schedules with Plasencia’s principal Act as contact person between hosting teachers and coordinators at New Village Girl’s Academy Consult with hosting teachers regarding questions they may have about training and working with their high school volunteer | Ongoing (10/2013-12/2013) 10/2013-11/2013 10/2013 10/2013 Ongoing (10/2013-12/2013) 2-4 times per month | 2.1, 3.2, 4.1, 4.2, 5.1 |

Project #6:  After School Program Liaison

| Major Activities To Be Accomplished | Timeline and Agreed Upon Evidence of Accomplishments | Standards Met |
| --- | --- | --- |
| Monitor specific program needs and provide feedback to coaches and site director Work with coachers in communicating with parents in an effort to maximize program benefits Support coaches by providing extra academic support to students and/or academic and behavior consultation Connect students who appear at risk of not meeting program requirements with school psychiatric social worker for possible intervention | Ongoing (8/2013-6/2014) Ongoing (8/2013- 6/2014) Ongoing (8/2013-6/2014) Ongoing (8/2013-6/2014) | 4.3, 5.4, 6.2, 6.3 |